## Sheet1
PROJECT NAME | Capstone Project |  | Bug Report Status for Guest and Admin Module
Reporter | Eugene |  | Pass | 53 | Defect | 0 | Major | 0 | Fixed | 54
URL | localhost/web/rems_copyright |  | Fail | 6 | Enhancement | 0 | Minor | 0 | Reopen | 0
|  |  | Pending | 0 | Task | 0 | Critical | 0
Ticket # | Description | Steps | Entry | Expected Results | Actual Results | Date | Pass / Fail | Type | Priority | Action | Notes
1 | check all links if working – user/guest/index.php | 1. go to rems_copyright/user/guest/index.php 2. click {;} REMS in nav bar 3. click Home in nav bar |  | redirect to home | redirect to home | 2016-02-26 | pass | success | none | fixed
2 |  | 4. click about in nav bar |  | redirect to about | redirect to about | 2016-02-26 | pass | success | none | fixed
3 |  | 5. click news & information in nav bar |  | redirect to news & information | redirect to news & information | 2016-02-26 | pass | success | none | fixed
4 |  | 6. click job opportunities in nav bar |  | redirect to job opportunities | redirect to job opportunities | 2016-02-26 | pass | success | none | fixed
5 |  | 7. click contact us in nav bar |  | redirect to contact us | redirect to contact us | 2016-02-26 | pass | success | none | fixed
6 |  | 8. click about the system in footer |  | redirect to about | redirect to about | 2016-02-26 | pass | success | none | fixed
7 |  | 9. click news & information in footer |  | redirect to news & information | redirect to news & information | 2016-02-26 | pass | success | none | fixed
8 |  | 10. click now hiring in the footer |  | redirect to job opportunities | redirect to job opportunities | 2016-02-26 | pass | success | none | fixed
9 |  | 11. click talk to us 12. click contact us |  | redirect to contact us | redirect to contact us | 2016-02-26 | pass | success | none | fixed
10 |  | 13. click check image file in footer |  | redirect to how to check image file | redirect to how to check image file | 2016-02-26 | pass | success | none | fixed
11 |  | 14. click convert resume to pdf |  | redirect to convert resume to pdf | redirect to convert resume to pdf | 2016-02-26 | pass | success | none | fixed
12 |  | 15. click read terms of use |  | redirect to terms of use | redirect to terms of use | 2016-02-26 | pass | success | none | fixed
13 |  | 16. click why did the operation failed |  | redirect to operation failed | redirect to operation failed | 2016-02-26 | pass | success | none | fixed
14 |  | 17. click the getchs footer |  | redirect to developers | redirect to developers | 2016-02-26 | pass | success | none | fixed | contents of the redirected page were not checked yet The priority is if all the links were working
15 | user/guest/index.php Skipped: 1. iApply 2. Exam Reason: input from other modules are required for this | 18. click iApply 19. click exam |  | - | - | 2016-02-27 | fail | skipped | high
16 | Admin Login | 20. click login from the nav bar |  | redirect to login page | redirect to login page | 2016-02-27 | pass | success | none | fixed
17 | reset login form | 21. fill up login form and click reset | username: admin Password: admin | clear fields in login form | clear fields in login form | 2016-02-27 | pass | success | none | fixed
18 | login as admin | 22. fill up login form and click login | username: admin123 Password: admin123 | failed to login Redirect to login form | failed to login Redirect to login form | 2016-02-27 | pass | success | none | fixed | What are the valid and invalid inputs?
19 |  | 23. fill up login form and click login | username: admin Password: admin | logged in as admin (gen calda) Redirect to admin page | logged in as admin (gen calda) Redirect to admin page | 2016-02-27 | pass | success | none | fixed
20 | Check all links and sub links if working - User/admin | 24. click {;} REMS 25. click Home |  | redirect to admin index page | redirect to admin index page | 2016-02-27 | pass | success | none | fixed | contents in the admin dashboard is insufficient
21 | Admin/maintenance/client | 26. click maintenace/client |  | redirect to browse client | redirect to browse client | 2016-02-27 | pass | success | none | fixed | pagination for this table is needed
22 | admin/maintenace/jobpostin | 27. click maintenance/job posting |  | redirect to browse jobs | redirect to browse jobs | 2016-02-27 | pass | success | none | fixed | pagination is needed
23 | admin/maintenace/exam | 28. click maintenace/exam |  | redirect to exam | redirect to exam | 2016-02-27 | pass | success | none | fixed | Warning: mysql_fetch_array() expects parameter 1 to be resource, boolean given in /opt/lampp/htdocs/web/rems_copyright/user/admin/maintenance/exam.php on line 115
24 | admin/maintenace/tpe of business | 29. click maintenance/type of business |  | redirect to type of business | redirect to type of business | 2016-02-27 | pass | success | none | fixed | pagination is needed
25 | Admin/transactions/client partnership | 30. click transactions/client partnership |  | redirect to client partnership | redirect to client partnership | 2016-02-27 | pass | success | none | fixed | validation is needed here
26 | admin/transactions/assess applicant | 31. click transactions/assess applicants |  | redirect to assesss applicants | redirect to assesss applicants | 2016-02-27 | pass | success | none | fixed | validation and pagination is needed
27 | admin/transactions/endorsed applicant | 32. click transations/endorsed applicant |  | redirect to endorsed applicant | redirect to endorsed applicant | 2016-02-27 | pass | success | none | fixed | pagination for this table is needed
28 | admin/transactions/employee | 33. click transactions/employee |  | redirect to employee | redirect to employee | 2016-02-27 | pass | success | none | fixed | check breadcrumb label, subtitle
29 | admin/transactions/performance evaluation | 34. click transactions/performance evaluation |  | redirect to performance evaluation | redirect to performance evaluation | 2016-02-27 | pass | success | none | fixed | pagination
30 | admin/transactions/reported employees | 35. click transactions/reported employees |  | redirect to reported employees | redirect to reported employees | 2016-02-27 | pass | success | none | fixed | pagination, what is the examined reports for?
31 | admin/reports/applicant report | 36. click reports/applicatn reports |  | redirect to applicatn reports | redirect to applicatn reports | 2016-02-27 | pass | success | none | fixed | pagination
32 | admin/reports/endorsement | 37. click reports/endorsement |  | redirect to endorsement | redirect to endorsement | 2016-02-27 | pass | success | none | fixed | pagination
33 | admin/reports/client | 38. click reports/client |  | redirect to client reports | redirect to client reports | 2016-02-27 | pass | success | none | fixed | pagination, not everything is printed
34 | admin/reports/employee | 39. click reports/employee |  | redirect to employee reports | redirect to employee reports | 2016-02-27 | pass | success | none | fixed | pagination
35 | admin/utilities/settings | 40. click utilities/settings |  | redirect to settings | redirect to settings | 2016-02-27 | pass | success | none | fixed | validation is needed here
36 | admin/queries | 41. click admin/queries |  | redirect to queries | redirect to queries | 2016-02-27 | pass | success | none | fixed
37 | admin/notifications | 42. click notifications |  | show notifications modal | show notifications modal | 2016-02-27 | pass | success | none | fixed | outputs are mixed
38 | admin/username | 43. click username in navbar |  | edit user info | not redirected | 2016-02-27 | fail | no module found | high |  | no module found
39 | admin/logout | 44. click logout |  | logout user | logout user | 2016-02-27 | pass | success | none | fixed
40 | Admin footer – client/browse client | 45. click browse clients in the footer |  | redirect to browse client | redirect to browse client | 2016-02-27 | pass | success | none | fixed
41 | Admin footer – client/add client | 45. click add client in the footer |  | redirect to add client | redirect to add client | 2016-02-27 | pass | success | none | fixed | validation is needed here
42 | Admin footer – client/update client | 46. click update client in the footer |  | redirect to update client information | redirect to update client information | 2016-02-27 | pass | success | none | fixed | validation is needed here
43 | Admin footer – job/browse jobs | 47. click browse jobs in the footer |  | redirect to browse jobs | redirect to browse jobs | 2016-02-27 | pass | success | none | fixed | pagination
44 | admin footer – job/add job | 48. click add job in the footer |  | redirect to add job | redirect to add job | 2016-02-27 | pass | success | none | fixed | validation is needed here
45 | admin footer – job/update job | 49. click update job in the footer |  | redirect to update job | redirect to update job | 2016-02-27 | pass | success | none | fixed | pagination
46 | admin footer – type of business/browse type of business | 50. click browse type of business in the footer |  | redirect to browse type of business | redirect to browse type of business | 2016-02-27 | pass | success | none | fixed | pagination
47 | admin footer – type of business/add new type of business | 51. click add new type of business in the footer |  | redirect to add new type of business | redirect to add new type of business | 2016-02-27 | pass | success | none | fixed | validation
48 | admin footer – type of business/update type of business | 52. click update type of business in the footer |  | redirect to update type of business | redirect to update type of business | 2016-02-27 | pass | success | none | fixed | validation
49 | admin footer – transactions/assess applicant | 53. click assess applicant in the footer |  | redirect to assesss applicants | redirect to assesss applicants | 2016-02-27 | pass | success | none | fixed | validation and pagination is needed
50 | admin footer – transactions/endorse applicant | 54. click endorse applicant in the footer |  | redirect to endorsedApplicant.php | redirected to a broken link (endorse.php) | 2016-02-27 | fail | error | medium
51 | admin footer – transactions/deploy applicant | 55. click deploy applicant in the footer |  | redirect to employedApplicant.php | redirected to a broker link (deploy.php) | 2016-02-27 | fail | error | medium
52 | admin footer – transactions/performance evaluation | 56. click performance evaluation from the footer |  | redirect to performance evaluation | redirect to performance evaluation | 2016-02-27 | pass | success | none | fixed | pagination
53 | admin footer – reports/client | 57. click client in the footer |  | redirect to client reports | redirect to client reports | 2016-02-27 | pass | success | none | fixed | validation
54 | admin footer – reports/applicant | 58. click the applicant in the footer |  | redirect to applicant report | redirect to applicant report | 2016-02-27 | pass | success | none | fixed | validation
55 | admin footer – reports/endorsement | 59. click endorsement in the footer |  | redirect to endorsement report | redirect to endorsement report | 2016-02-27 | pass | success | none | fixed | validation
56 | admin footer – reports/employee | 60. click employee in the footer |  | redirect to employee reports | redirect to employee reports | 2016-02-27 | pass | success | none | fixed | validation
57 | admin footer – utilities/settings | 61. click settings in the footer |  | redirect to settings | redirect to settings | 2016-02-27 | pass | success | none | fixed | validation
58 | admin footer – utilities/website content | 62. click website content |  | redirect to website content | broken link | 2016-02-27 | fail | error | medium
59 | admin footer – queries/queries | 63. click queries in the footer |  | redirect to queries | redirect to queries | 2016-02-27 | pass | success | none | fixed
60 | admin footer – developers/view developers | 64. click view developers in the footer |  | redirect to developers | redirected to a broken link (developers.php) | 2016-02-27 | fail | error | medium